## Test Tracker
Title | Description/Steps to Reproduce | Expected Result | Date | Branch | Priority | Reporter | Assigned Developer | Estimate | Actual | Status | Note
Crash on Enemy Collision | 1) Walk into enemy 2) Game crashes | The appropriate amount of damage is applied to the player and enemy. The player should also see particles fly out of the enemy and themselves with air friction. | 2024-10-11 | main | P0 | Arshvir | Asher |  |  | Done
Wall overlap causes crash | 1) Create walls that overlap 2) Game crashes | Game should not crash | 2024-10-11 | main | P0 | Arshvir | Asher |  |  | Done
Enemy spawns out of bounds | 1) Kill enemy 2) Will sometimes spawn out of bounds | Enemies can only spawn within walls/defined game bonderies | 2014-10-12 | main | P2 | Arshvir | Asher |  |  | Done
Character moves slowly down to the right | 1) Launch game 2) Observe char moves down and to the right | Character should stay still if no input is being given | 2024-10-12 | main | P2 | Arshvir | Asher |  |  | Done
Character goes through all rooms in a direction if they touch the up/right door | 1) walk into the right door 2) observe you are on the last room possible on the right/top | Should only move one room at a time | 2024-11-03 | main | P1 | Matt | Matt |  |  | Done
Shooting enemy shoots at you upon entering a room even if out of range | 1) walk into a room 2) Observe sometimes an enemy across the room will immediately attempt to shoot you | Enemies should only attempt to attack you if you are within range. So if an enemy is across the room they won't attack you | 2024-11-03 | main | P2 | Arshvir | Patrick |  |  | In progress
Enemies and obstacles sometimes spawn on top of eachother | 1) start game 2) observe enemy has spawned on a obstacle and is twitching or stuck 3) observe dropped items also become inaccessible | enemies should never spawn on obstacles | 2024-11-03 | main | P2 | Arshvir | Matt |  |  | Done
Enemy animations stop working after one enemy is killed | 1) start game 2) kill an enemy 3) get hit by enemy and observe no animation plays | animations should not stop working after player kills an enemy | 2024-11-03 | main | P2 | Kelcy | Kelcy |  |  | Done
Items in UI are offset incorrectly | 1) start game 2) pick up 2 items 3) observe that items aren't fitting into boxes | items should fit into boxes | 2024-11-03 | main | P2 | Asher | Kelcy |  |  | Done
Picking up items tanks framerate | 1) start game 2) pick up item 3) observe framerate drops | items should not tank framerate when picked up | 2024-11-03 | main | P1 | Matt | Kelcy |  |  | Done
when player is dying and pause scene is active, pause scene is dimmed | 1) start game 2) die 3) pause game and observe pause screen dims | pause screen should not dim | 2024-11-03 | main | P2 | Asher | Asher |  |  | Done
Health is displayed as negative after death sometimes | 1) start game 2) reach 1 HP 3) get hit 4) pause wait a few seconds 5) unpause and get hit 6) observe HP enters negatives | HP should never be neagative | 2024-11-03 | main | P3 | Asher | Asher |  |  | Done | Cooldown doesn't pause on game pause
menu buttons clickable through help screen | 1) launch game 2) enter help menu 3) click where start game would be and observe that the game starts | main menu buttons should not be clickable through help screen | 2024-11-03 | main | P2 | Asher | Asher |  |  | Done
Floor items can spawn on top of each other | 1) launch game 2) check all rooms until you find the bug 3) repeat if necessary | Items should not overlap when they spawn - looks bad for graphics | 2024-11-03 | main | P2 | Matt | Matt |  |  | Done
Items and NPC's interactables can be used through walls | 1) launch game 2) kill enemy to drop item 3) go to another room and stand on the same part of the room where the item is 4) press 'E' and see item in the other room has been picked up | Should not be able to pick up items in other rooms or talk to NPC's in other rooms | 2024-11-18 | ASHER-HELL-MERGE | P2 | Matt | Asher |  |  | Done
Self destruct text appears too soon on final boss | 1) launch game 2) get to third stange of boss 3) Self destruct text appears | Self destruct text should not appear until second last stage and disapear after the second last stage | 2024-11-18 | ASHER-HELL-MERGE | P2 | Asher | Asher |  |  | Done
Items can be used multiple times as it's floating up | 1) launch game 2) kill enemy to drop item 3) pick up item 4) As it is floating up spam 'E' 5) item is picked up multiple times | Item should not be picked up multiple times | 2024-11-18 | main | P2 | Asher | Asher |  |  | Done
Items on the ground are not saved | 1) launch game 2) kill enemy to drop item 3) save quit 4) reload 5) item is missing | Item should presist | 2024-11-18 | main | P2 | Asher | Patrick |  |  | Done
Going through multiple doors at once when colliding with door | 1) launch game 2) Try going through bottom door 3) Get taken all the way to the lowest room 4) Could also result in getting hit by none active enemies which appear invisible | Should just go to next immediate room Non-active enemies should not do damage to the player | 2024-11-18 | main | P1 | Matt | Asher |  |  | Done
Self destruct text appears over top of enimies | 1) launch game 2) get to second last stage of final boss 3) self destruct text is overtop of player/enemies | Text should be below player and enemies | 2024-11-18 | main | P2 | Kelcy | Asher |  |  | Done
Boss 2 not working | 1) launch game 2) get to boss 2 3) observe boss is unressponsive and nothing spawns | 4 waves of enemies should spawn | 2024-11-19 | main | P2 | Matt | Arshvir |  |  | Done
Music not turning on when fighting bosses | 1) launch game 2) get to boss 1 3) observe no music plays | fighting music should start playing | 2024-11-19 | main | P2 | Arshvir | Arshvir |  |  | Done
when talking to an npc, if player is in the middle of movement, movement is not stopped when dialogue ends and player will move without pressing anything | 1) launch game 2) get to an NPC 3) move towards NPC 4) click E while moving 5) observe character keeps moving | character should stop moving when in dialogue | 2024-11-19 | main | P2 | Asher | Asher |  |  | Done
X not scrapping item | 1) launch game 2) get to an item 3) press X 4) observe that item is not being scrapped | item should be scrapped and disspear | 2024-11-19 | main | P2 | Kelcy | Asher |  |  | Done
Note on F1: High or Low